## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Collecting data form users | 8
Faculty will post questions |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Student wil answer questions |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Maintains answers given by students |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
Creation of Outcomes of different courses | 10
Faculty will float courses |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Faculty will post outcomes for the courses |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Faculty will post questions for each outcome |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Student will register for the courses |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
Student will answer outcomes |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
Registration | 5
Enter personal details |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Check the validity of the details |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Take username and password |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Check if username already present |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
Login | 5
Take username and password |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Check if username and password match |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Feedback | 3
Check student answers |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Give feedback |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Total |  |  |  | 60 | 48 | 47 | 32.5 | 16.5 | 15 | 10
Create a Sprint Backlog in Smartsheet